|  | PROCUREMENT CONTRACT |
| --- | --- |
|  | ☒Service – ☐Supplies |
|  | Number: 26-MR6514 |
|  | Object of the contract: Provision of Engineering Consultancy Services (Project manager) for SECFRON III including site surveys, investigations, engineering design, preparation of technical studies, drawings, Bills of Quantities, technical specifications, cost estimates, complete tender documents preparation, technical management, control, and supervision of works and assistance during provisional acceptance, final acceptance, and handover of infrastructure component works. |
|  | MAXIMUM AMOUNT OF THE CONTRACT: state here the maximum amount of all services/supplies that may be delivered under the contract (prices of firm items + max amount of purchase order items) |
| Award date: XXXX. This Contract is subject to the French Public Procurement Code in its latest version in force as enacted by Order No. 2018-1074 issued on 26 November 2018 and its Implementation Decree No. 2018-1075 issued on 3 December 2018 constituting the regulatory aspects of the Public Procurement Code (“CCP”). It is awarded by means of open tender in application of L. 2124-2, R. 2161-2, R. 2161-3, R. 2161-4 and R. 2161-5 of CCP |

TABLE OF CONTENTS

special conditions – commitment procedure	5

ARTICLE 1:	DESIGNATION OF THE CONTRACTORS	8

ARTICLE 2:	Object of the contract	8

ARTICLE 3:	Contractual documents	9

3.1 Form of the Contract	11

3.2 Term of the Contract	11

3.3 Commencement and deadline of service provision	12

ARTICLE 4:	Construction budget and REMENURATION OF THE PROJECT OWNER	13

4.1 Construction of works budget	13

ARTICLE 5:	inspection and acceptance activities	17

ARTICLE 6:	FINANCIAL EXECUTION OF THE CONTRACT	17

6.1.  Form of prices	17

6.2.	Advance	17

6.4.	Presentation of payment demands	21

6.5.	Bank transfer	22

6.6.	Value added tax (VAT)	22

6.7.	Taxes and duties	22

ARTICLE 7:	Specific terms of execution	22

7.1.	Relationship with Expertise France	22

7.2.	Project progress meetings	22

7.4.	Rights and duties of the CONTRACTOR	23

7.5.  Deliverables table	23

7.6.	Place of execution	27

7.7.	Language of the Contract	27

7.8.	Commitments of the Contractor	27

7.9.	Confidentiality	27

7.10.	Provision of documents	28

7.11.	Contact person and communication	28

7.12.	Undertaking against deforestation	29

ARTICLE 8:	REVIEW CLAUSE	29

8.1.	Modifications Authorized under the Contract	29

8.2.	Classification of Modifications during the Study Phase	30

ARTICLE 9:	ENGAGEMENT OF THE PROJECT OWNER	31

ARTICLE 10:	RESPONSABILITY	33

ARTICLE 11:	INSURRANCE	34

12	Similar services	35

13	penalties	35

14	intellectual property	36

Definitions	36

Ownership of results	37

Exploitation of results	37

Licensing of pre-existing rights	37

Guarantees	38

Image rights	38

15	Termination of the CONTRACT	38

General terms of performance	38

Procedure	39

16	SUSPENSION OF SERVICES IN CASE OF UNFORESEEABLE CIRCUMSTANCES	39

17	MEASURES TAKEN EX OFFICIO	39

18	safety and security measures and responsabilities	40

19	ethics	40

20	Administration of personal data	40

21	Dispute resolution - applicable law	41

22	Derogation from the CCAG	42

23	AUDIT	42

24	Final provisions	43

Declaration	43

Annex 1: Technical Specifications	46

# special conditions – commitment procedure

Between:

EXPERTISE FRANCE SAS 40, boulevard de Port Royal - 75005 PARIS, France A simplified joint-stock company with share capital of €828,933 registered under the following numbers: - SIRET no.: 808 734 792 00035 - Intra-community VAT number: FR36 808734792 Represented by Mr Jérémie PELLET, Managing Director, of the first part,

and:

co-contracting party’s name (TO BE COMPLETED) IF ONE CANDIDATE (Hereafter the “Contractor”) Article 1.1 – Sole tenderer ❑ Mr / Mrs … acting in their personal name. ❑ The company: - Registered office address:____________________________________________________ - Registration number at the trade and companies registry:____________________________ - Intra-community VAT no. (as applicable): ______________________________________________ (Name and role of the company’s representative) Address:____________________________________________________________________________ Phone / Mobile:_________________________________________________ Email:_____________________________________________________________________________ Hereinafter referred to as “the Project managers”.

| co-contracting party’s name IF CONSORTIUM (Hereafter the “Contractor”) Represented by: (name, first name, and position) of the second part, |
| --- |
| Composition of the consortium |
| Type of economic operator’s consortium: Tick the corresponding box joint and several OR joint with joint and several representative |
| CO-CONTRACTOR NO.1 (leader of the consortium) |
| Full official Name |  |
| Represented by: (name, first name, and position) : |  |
| Official legal form of the co-contractor (or joint contractor) |  |
| Full official adress |  |
| Legal registration number |  |
| VAT registration number |  |
| Contact |  |
| CO-CONTRACTOR NO.2 |
| Full official name |  |
| Represented by: (name, first name, and position) : |  |
| Official legal form of the co-contractor |  |
| Full official address |  |
| Legal registration number |  |
| VAT registration number |  |
| Contact |  |

(Hereafter referred to collectively as the “Parties“)

Whereas:

In the context of the cooperation project (Contribution Agreement 700003763), hereafter the “Main Contract” (donor contract) signed on 2024 between The European Union and Expertise France, covering “EU support to Jordanian Armed Forces (SECFRON III)” Expertise France asks the Contractor, which accepts the same, to perform the services and deliver the services under the Contract as set out in the attached technical annex entitled “Term of Reference and Technical Specifications”.

In the light of the foregoing, the following is agreed:

- DESIGNATION OF THE CONTRACTORS

This Contract is a public project managers contract in accordance with Article 2 below.
It is entered into between:

- Expertise France S.A.S, hereinafter referred to as the “Contracting Authority” or the “Delegated Contracting Authority”, acting in the name and on behalf of the Jordan Armed Forces, hereinafter referred to as the “Project Owner”;

- and the Contractor designated in Article 2.1 of the Contract Agreement, hereinafter referred to as the “Project manager)” under this Contract.

Pursuant to Article R.2182-4 of the French Public Procurement Code, the provisions of this Contract shall take effect as from the date of receipt of its notification by the Project manager

- Object of the contract

The object of this Contract (hereafter the “Contract) is for the provision of ‘Project managers’, Scheduling, Management and  Coordination (SMC), The term of reference and technical specification  describes the missions to be carried out by the Contract holder.

As an indication, the work operation is estimated at € 5,564,000 excluding VAT. The start of the work is desired by July 2027,the place where the project will be performed  is Jordan – Rewashed “ Karameh area “

The CONTRACTOR shall provide all professional engineering consultancy services required for the planning, investigation, design, tender documentation, technical supervision and contract implementation support for the permanent infrastructure components identified under the Project, as further described in the Terms of Reference (ToR) and the Technical Specifications (TS) forming an integral part of this CONTRACT.

The “ Project manager “ shall include:

- Site reconnaissance and engineering investigations.

- Topographical and utility surveys.

- Geotechnical investigations, where required.

- Engineering design and multidisciplinary coordination.

- Preparation of drawings, technical specifications and Bills of Quantities (BoQs).

- Preparation of engineer's cost estimates.

- Preparation of complete tender documentation.

- Technical support during the tendering process.

- Review of Contractor execution documents.

- Technical management, monitoring and supervision of construction works.

- Assistance during testing, commissioning, provisional acceptance, final acceptance and project handover.

- Preparation and verification of as-built documentation and close-out documents.

The detailed scope of services, responsibilities, deliverables and implementation requirements shall be as defined in the attached Terms of Reference and Technical Specifications (Annex 1).

- Contractual documents

The Contract is composed of the contractual documents set out below in decreasing order of priority:

- This document and its annexes:

- Terms of Reference and Technical Specifications;

- Service Contract;

- Tender Rules;

- Work Program calendar ;

- Financial annex;

- Request for Proposal application ;

  - The program including the detail of the financial envelope retained by the  contracting authority and allocated to the works, as well as any annexes thereto;

- The consortium representative designation; The Code of Conduct of Expertise France (available at https://www.expertisefrance.fr/en/ethics-and-transparency );

- Annex 2 (DAJ_M050) covering the processing of personal data in the event of GDPR data processing (collection of personal data on behalf of Expertise France).

  - Any written and graphical documents provided by the contracting authority during the consultation;

  - Special subcontracting deeds and their possible amendments, subsequent to the contract notification

- General administrative clauses applicable to public procurement for Project managers contracts (CCAG-MOW), approved by the decree of March 30, 2021, subject to the exceptions set out in the Contract and The CCAG - General administrative clauses applicable to public procurement for Public Work contracts, by the decree of March 30, 2021 (available at the following link: https://www.legifrance.gouv.fr/jorf/id/JORFTEXT000043310778).

- The Contractor’s bid, is consisting of written and possibly graphical documents, including any additions made in case of negotiation and clarification, as well as a detailed table of tasks distribution by mission elements if the offer was submitted by a consortium;

These documents constitute the entirety of the agreement between the Parties with regard to the Contract. They supersede all verbal and written communications, procedures, agreements, commitments, guarantees and settlements referring to its object and facts that may have been made by or on behalf of a Party to the other Party before the notification date. These documents are acknowledged by the Parties to represent the sole and complete expression of the terms of their agreement.

Without prejudice to the general rules applicable to administrative contracts, any modification to the Contract or the waiver of any right resulting from the Contract must be covered by an amendment signed by a duly authorized representative of each Party.

General characteristics of the Contract

## 3.1 Form of the Contract

The Contract is a public contract for services lump sum prices, based on the following items (phase):

| Item 1 – phase 1 | Site Assessments, Design Development, and Works Tender Technical Dossier : Mission 1: Preliminary Design Studies (PDS) Mission 2: Technical design studies (TDS) Mission 3: Preparation consultation documents (OCD), assistance for the analysis of the bids |
| --- | --- |
| Item 2 – phase 2 | Technical Management, Control, and Supervision of Works : Mission 4: VISA for Execution and synthesis studies (VISA) Mission 5: Works Contract Execution Direction (WED) |
| Item 3 – phase 3 | Provisional Acceptance, Final Acceptance, and Handover : Mission 6: Assistance to reception operations (ARO) Mission 7: As-Built Documentation (ABD) |

The Contract is not broken down into batches as the services provided for in this Contract are not subject to subdivision into separate work packages.

## 3.2 Term of the Contract

The term of the Contract comes into force on its notification date. Under no circumstances may performance commence before the notification date of the work order.

Notification of the Contract shall not constitute commencement of the missions.

The missions and deliverables will begin on the date specified in the start-up work order notified to the Contractor by Expertise France.

Each task begins upon receipt of a formal work order authorizing its execution.

The duration of the Contract runs from the date of notification until the signature of the (CR of final handover of the works which corresponds to the completion of the project manager ‘s mission. The defects liability periods (DLP) applicable to construction contracts it’s transferred to the local beneficiary. The Guarantee of perfect completion and any other warranty periods applicable under the Contract can be extended if any defects are identified during the final handover. Extension of guarantee of perfect completion period does not extend the term of the contract.

The Contract shall expire at the time of submission of as-built documentation and project handover report, and in any case after all services have been delivered by the Contractor and all rights and obligations of the Parties resulting from the Contract have been extinguished. If all or some of the services remain outstanding by the specified period, the Contractor must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

The overall estimated duration for the execution of the Contract is 24 months and is broken down as follows:

| Item Number | Duration | Missions | Item details |
| --- | --- | --- | --- |
| Item 1 – phase 1 | 5 Months | Site Assessments, Design Development, and Works Tender Technical Dossier : |  |
|  |  | Mission 1: Preliminary Design Studies (PDS) | Preparation of drawings, BoQs, project tracking schedules, technical specifications and progress tracking check-lists/tools |
|  |  | Mission 2: Technical detailed design studies (TDS) |  |
|  |  | Mission 3: Preparation consultation documents (OCD), assistance for the analysis of the bids | Provide technical assistance to the procurement/s preparation, provide technical assistance in bid evaluation process; |
| Item 2 – phase 2 | 16 Months | Technical Management, Control, and Supervision of Works : |  |
|  |  | Mission 4: VISA for Execution and synthesis studies (VISA) | : Supervise and monitoring of the rehabilitation projects. During this phase, the MoW expected to undertake various activities such as: production monthly progress reports, participation in technical meetings, project handover and provisional acceptances etc. |
|  |  | Mission 5: Works Contract Execution Direction (WED) |  |
| Item 3 – phase 3 | 3 months | Provisional Acceptance, Final Acceptance, and Handover : |  |
|  |  | Mission 6: Assistance to reception operations (ARO) | months Post Execution phase: Conduct inspections to the completed works, capacity building training and provisional acceptance/s |
|  |  | Mission 7: As-Built Documentation (ABD) |  |

## 3.3 Commencement and deadline of service provision

The service provision deadline under this Contract is 14 days from the award date of this contract to the Contractor.

If all or some of the services remain outstanding within the specified deadline, the Contractor must immediately take all necessary steps to complete delivery without being able to claim any remuneration in this regard.

After the acceptance of the works, the project managers submits the declaration certifying the completion and conformity of the works to the project beneficiary (Jordan armed forces JAF ), along with the certificates related to compliance with construction regulations, when required.

The declaration of completion and conformity is prepared and signed by the project managers when the project owner (Jordan armed forces JAF and Expertise France) have received   the works, according to Art. 5 of the present Contract.

3.4 Guarantee of perfect completion

The guarantee of perfect completion applies to:

  - Defects and non-conformities that were apparent at the time of acceptance and were the subject of explicit reservations; and

  - Defects that appear within one (1) year following the date of acceptance of the works.

  - This guarantee covers all defects, regardless of their nature, origin, or severity, including but not limited to: Construction defects, Non-conformities, Poor workmanship

The guarantee does not cover, defects resulting from normal wear and tear or regular use, and apparent defects not subject to reservation at the time of acceptance.

- Construction budget and REMENURATION OF THE PROJECT OWNER

## 4.1 Construction of works budget

Upon signature of this Contract, the Project Owner (Jordan Armed Forces JAF ) will receive the final project with the main construction works budget supervised by the Project Manager (contractor -ECC) of an estimated amount of five million five hundreds sixty four thousand euros and zero cents (5.564.000 €) excluding VAT.

4.2 Remuneration of the project manager (Contractor (ECC) )

4.2.1 – Lump Sum Remuneration

The remuneration under the contract is a lump sum for the performance of the services described in the documents of the Contract.

The Project manager (contractor -ECC ) may not receive any other remuneration from a third party in connection with the execution of the operation.

The amounts used as a basis for calculating changes in the remuneration of the project manager, as well as for monitoring commitments, are expressed in euros excluding taxes.

4.2.2 – Provisional Lump Sum Remuneration

The lump sum remuneration specified in the contract agreement is provisional, in accordance with Articles R. 2112-18 and R. 2432-7 of the French Public Procurement Code.

The amount of the provisional lump sum remuneration has been determined taking into account the information available to the project manager at the time of the award of the contract, such as:

- the scope of services defined by the documents of Contract;

- the work program calendar;

- the portion of the estimated financial envelope allocated to the works, as set by the delegated project beneficiaries (Jordan armed forces JAF );

- elements of complexity related to local constraints, project integration into its environment, the nature and specificity of the project, and resulting contractual requirements;

- deadlines for Project manager (contractor -ECC) studies and the time allowed for review by the delegated project beneficiaries (Jordan armed forces JAF );

- the expected modes of awarding and tendering the works contracts;

- the anticipated duration of the works and their possible phasing;

- any possible subdivision of the operation into several phases of implementation;

- continuity of the operation;

- insurance costs borne by the Project manager.

This provisional lump sum may be modified in the event of circumstances affecting the execution of the contract before the determination of the final lump sum, in accordance with Articles R. 2194-2, R. 2194-5, R. 2194-7 and R. 2194-8 of the French Public Procurement Code, and under the procedures set out in Articles 7.1 and 7.2 of the CCAP.

Furthermore, the prices are deemed to include:

- all ancillary costs and expenses related to the performance of the services under this contract;

- all applicable taxes, parafiscal charges, or other charges relating to the services;

- all services specified in the TORs or in the annex “program of the Contracting Authority”;

- all deliverables listed in the TORs or the annex “program of the Contracting Authority”;

- all telephone calls and meetings;

- all travel expenses and administrative costs relating to the services;

- administrative and commercial follow-up;

- The amounts also include the transfer of intellectual property rights.

In the case of a consortium of companies, the remuneration of the lead partner includes the coordination of services not performed by them but assigned to their partners. This includes scheduling, management, and monitoring to ensure the proper performance of the contracts.

In the case of subcontracting, the prices are deemed to cover the coordination and supervision costs incurred by the Contractor for its subcontractors, as well as any consequences resulting from potential failures on their part.

The prices are therefore established as inclusive of all subjects normally required for the execution of the services covered by the Contract.

The Contractor is required to coordinate, under the supervision of Expertise France with the Project Owner (Jordan armed forces JAF), with other service providers (such as Assistance to the delegated contracting authority). The Project Owner may participate, at its discretion, in coordination meetings dealing with interface issues involving these external parties. These costs are included in the lump-sum remuneration.

In addition to the specific services for each phase and mission element defined below, the Contractor undertakes, throughout the operation, to include in its pricing:

- Preparing for and attending monthly meetings organized by Expertise France/Project Owner;

- Attending all other meetings organized by the Expertise France/Project Beneficiaries;

- Preparing and submitting a meeting report for each meeting within 48 hours before the next meeting.

The research, acquisition, and compilation of historical, technical, administrative, or legal data necessary for carrying out the assignments under the control of Expertise France in coordination with the Project Owner (Jordan armed forces JAF) are included in the lump-sum fee, regardless of the origin of the data.

Where applicable, all existing documents will be provided to the Contractor at the start of the assignments. These documents are intended to help the Contractor assess the general scope of the Contract and estimate the necessary intervention.

For all documents submitted to the Contractor, Expertise France may at any time request updates, whether regular or occasional. These updates must be considered in the Contractor’s price offer and shall in no case give rise to additional remuneration under the Contract.

4.2.3 – Determination of the Estimated Cost of the Works and the Final Lump Sum Remuneration

The lump sum remuneration is exclusive of any other fee or reimbursement of expenses in respect of the same mission. The final lump sum is deemed to be established on the basis of the economic conditions prevailing in month Mo at the completion of the detailed design stage.

The provisional remuneration corresponds to the lump sum amount undertaken by the project manager upon notification of the present contract.

The provisional remuneration becomes final upon acceptance by the delegated Project Owner (Expertise France) of the detailed design and upon the project manager’s commitment to the estimated cost of the works.

4.2.4 – Transition to the Final Lump Sum Remuneration

Upon submission of the detailed design, the Project managers commits to the estimated cost of the works.
This commitment is documented in writing, duly signed, and formally transmitted to Expertise France  and the Project Owner (JAF ) together with the detailed design, and must include:

- the name and reference code of the project;

- the name of the the project manager’s (contractor -ECC )or the representative of the the project manager’s (contractor -ECC );

- the estimated cost of the works.

To move from provisional to final remuneration, the parties agree to apply the following formula:

Final remuneration = Definitive estimate of the works cost × remuneration rate indicated in the Financial annex or Contract.

The fixed price of each phase corresponds to the amount Expertise France undertakes to pay following satisfactory completion, review, validation, and acceptance of the corresponding services and deliverables

| ITEM |  | TYPE OF AMOUNT | AMOUNT |
| --- | --- | --- | --- |
|  | Phase 1 |  |  |
| P1 - Site Assessments, Design Development, and Works Tender Technical Dossiers: 30 % from the contract value | Mission 1: Preliminary Design Studies (PDS) 6 % from the contract value | Fixed price | XXXX € exc. VAT. |
|  | Mission 2: Technical design studies (TDS) 16 % from the contract value |  | XXXX € exc. VAT. |
|  | Mission 3: Preparation consultation documents (OCD), assistance for the analysis of the bids 8 % from the contract value |  | XXXX € exc. VAT. |
|  | Phase 2 |  |  |
| P2 - Technical Management, Control, and Supervision of Works 60 % from the contract value | Mission 4: VISA for Execution and synthesis studies (VISA) 10 % from the contract value | Fixed price | € exc. VAT. |
|  | Mission 5: Works Contract Execution Direction (WED) 50 % from the contract value (3.125%per month for 16 months ) |  | € exc. VAT. |
|  | Phase 3 |  |  |
| P3 - Provisional Acceptance, Final Acceptance, and Handover 10 % from the contract value | Mission 6: Assistance to reception operations (ARO) 4 % from the contract value | Fixed price | € exc. VAT. |
|  | Mission 7: As-Built Documentation (ABD) 6 % from the contract value |  | € exc. VAT. |
| MAXIMUM AMOUNT OF THE CONTRACT |  |  | € exc. VAT. |

Remuneration after the detailed master work   is calculated as a percentage. It is established by amendment.

- inspection and acceptance activities

The verification and acceptance of services shall be carried out in accordance with Chapter 4 of the CCAG-MOE, based on the weekly progress reports and photographs provided.

Inspection activities will be carried out by:

- the Project manager of Expertise France.

- the infrastructure expert of Expertise France.

Any lack of response from Expertise France shall not equate to tacit acceptance of services or supplies.

- FINANCIAL EXECUTION OF THE CONTRACT

## 6.1.  Form of prices

Prices are firm and non-revisable.

## Advance

EF will not provide any advance payment under this contract, and all expenses required by the project managers must be covered by the firm before any interim payment is made.

  - Performance Guarantee Withholding

In accordance with Articles R.2191-32 to R.2191-41 of the French Public Procurement Code, a performance guarantee withholding is applied to ensure the proper execution of the services provided under this contract, as well as the repair of any defects or shortcomings identified during the defects liability period.

    - Amount of the guarantee withholding
The amount of the performance guarantee withholding is set at 5% of the initial contract amount, increased, where applicable, by the amount of any amendments. This rate is reduced to 3% for SMEs.

    - Substitution of the guarantee withholding by a bank guarantee
Upon notification of the contract, the contractor must provide either an on-demand guarantee (garantie à première demande) or a joint and several surety, in accordance with Article R.2191-36 of the Public Procurement Code.
This bank guarantee must be issued in the name of the Contracting Authority:

    - Expiration of the bank guarantee
the bank guarantee issued in the name of the Contracting Authority shall expire at the end of the defects liability period, provided that the contractor has fulfilled all obligations and repaired, where applicable, any identified defects.
The guarantee or surety must be provided after notification of the contract and before the payment of the first instalment.

    - Consequences in the event of defects or shortcomings
In the event that defects or shortcomings are identified during the defects liability period, the Contracting Authority may, after a formal notice has remained without effect, call upon all or part of the guarantee or surety to cover the costs necessary for the repair of such defects.

    - Payment procedure

| Phase 1: Site Assessments, Design Development, and Works Tender Technical Dossier : 30 % from the contract value | Payment |
| --- | --- |
| Mission 1: Preliminary Design Studies (PDS) 6 % from the contract value | € exc. VAT. |
| Mission 2: Technical design studies (TDS) 16 % from the contract value | € exc. VAT. |
| Mission 3: Preparation consultation documents (OCD), assistance for the analysis of the bids 8 % from the contract value | € exc. VAT. |
| Phase 2: Technical Management, Control, and Supervision of Works : 60 % from the contract value | Payment |
| Mission 4: VISA for Execution and synthesis studies (VISA) 10 % from the contract value | € exc. VAT. |
| Mission 5: Works Contract Execution Direction (WED) 50 % from the contract value (Monthly progress ) Avg 3.125 % per month | € exc. VAT. |
| Phase 3: Provisional Acceptance, Final Acceptance, and Handover: 10 % from the contract value | Payment |
| Mission 6: Assistance to reception operations (ARO)4 % from the contract value | € exc. VAT. |
| Mission 7: As-Built Documentation (ABD) 6 % from the contract value | € exc. VAT. |

Each payment milestone shall be subject to review, validation, and acceptance by Expertise France.

The fixed price of each phase corresponds to the amount Expertise France undertakes to pay following satisfactory completion, review, validation, and acceptance of the corresponding services and deliverables

- Periodic Report

The periodic report, drawn up by the Contractor, indicates the services performed since the beginning of the Contract, by reference to the elements of the assignment.
It serves as the basis for the preparation, by the Contractor, of the draft interim statement to which it must be attached.

- Draft Interim Statement

The Contractor shall submit a draft interim statement to Expertise France on a monthly basis.

- Interim Statement

The interim statement reflects the amount due from the start of the Contract up to the end of the relevant period.
This amount is calculated at base prices, excluding VAT. It is established from the draft interim statement and includes the following:

- The evaluation, at base prices, of the portion of remuneration payable in respect of the services performed;

- Any applicable penalties and deductions.

The payment of an interim invoice does not constitute acceptance, even partial, of the services under the Contract, and does not release the Contractor from any of its obligations under the Contract and the related task(s).

- Final Payment

Upon completion of its assignment (ABD), the Contractor shall submit to Expertise France a request for the final payment, in the form of a draft final statement.

- Final Statement

The final statement, establishing the remuneration at base prices, excluding VAT, due for the full performance of the assignment, shall include:

- The lump-sum remuneration indicated in the draft final statement prepared by the Contractor;

- Any penalties or deductions applicable to the Contractor in accordance with Article 9 of this Contract.

- General Statement – Balance Status

Expertise France shall prepare the general statement within a maximum of 30 days.

The general statement shall include:

- The final statement described above;

- A summary of interim payments as approved by Expertise France;

- The base price amount, excluding VAT, of the balance due, calculated as the difference between the final statement and the preceding statements;

- The balance payable to the Contractor;

- A recap of the interim payments already made and the balance due, which together constitute the total general statement amount.

Expertise France shall notify the Contractor of the general statement and the balance status.

The general statement shall become final upon acceptance (signature) by the Contractor.

    - Payment terms and late payment interest

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

Overall payment terms for monies due under the Contract are thirty (30) days maximum from the date of receipt of the complete invoice, including all supporting documentation, or the date of service acceptance if this date is later. Any missing document will prevent payment.

If these payment terms are not respected, Expertise France will pay late payment interest to the Contractor pursuant to Article R. 2192-10 et seq. of the CCP on the fight against late payment in public procurement contracts. The rate applied shall be the interest rate of the European Central Bank for its main and most recent refinancing operations, as applicable on the first day of the semester of the calendar year during which late payment interest started to accrue, plus eight percentage points.

The amount of the fixed indemnity to cover collection costs is set at forty (40) euros and will be systematically paid in addition to late payment interest. Interest below €40 shall not be mandated.

## Presentation of payment demands

In addition to the legal notices (intracommunity VAT no.), invoices relating to the Contract must contain the following information:

- Company name, address and registered office of the Contractor;

- Registration number of the Contractor (SIRET or equivalent);

- Bank account details;

- Reference number of the Contract;

- The reference and title of the cooperation project concerned (if applicable);

- Clear and accurate description of the equipment/supplies sold and/or services performed;

- If the Contractor’s bank details are not stated on invoices, it must provide a statement or certificate of bank or post office account details, with the third-party form duly completed in all cases.

Invoices are to be sent to the following address: anas.alaqabani@expertisefrance.fr

Invoices for advances must be accompanied by the corresponding supporting documentation validated by Expertise France.

Invoices for balances (partial definitive payments) must be accompanied by a copy of the acceptance decision for the corresponding services and/or supplies.

Any missing document will prevent payment.

## Bank transfer

Payment for invoiced services will be made to the bank account identified in the third-party sheet.

Payment is always made out in the name of the issuer of the invoice or of the expense reimbursement request.

## Value added tax (VAT)

The Contractor must state the VAT rate applicable to the transaction or, as applicable, its VAT exemption by stating on the invoice the relevant provisions of the French General Tax Code or those of Directive 2006/112/EC of 28 November 2006.

Any Contractor benefitting from exemption must state “VAT exempt” in accordance with the rules that apply to it.

## Taxes and duties

The Contractor shall be directly responsible for all taxes and duties that may be levied against it under the Contract, both in the country of its registered office and in those of project implementation.

- Specific terms of execution

## Relationship with Expertise France

All studies entrusted to the Contractor shall be carried out in close and continuous collaboration with Expertise France and its experts. To ensure effective cooperation, the Contractor shall organize itself to provide overall coordination and maintain a transversal oversight of all missions.

Expertise France shall communicate through a single point of contact who will coordinate with the various individuals involved within the Contractor’s team across all missions.

Expertise France must have access at all times to all technical and financial information necessary for control purposes.

## Project progress meetings

During both the study and construction phases, periodic progress meetings shall be held as needed, with a minimum frequency of one progress meeting per month.

A monthly project review meeting shall also be organized, during which all aspects of the operations will be reviewed: architecture, technical matters, scheduling, financial, land, political, communication, etc.

These meetings shall be chaired by the Contractor, who must send an agenda 48 hours before the meeting, draft the minutes, and distribute them within 48 hours after each meeting.

These meetings are included in the Contractor’s prices stated in the present Contract.

  - Relationship with contractors

If a dispute arises during or following a mission carried out by the Contractor between a Contractor and Expertise France, the latter shall request the Contractor to intervene in order to assist in defending its interests.

The Contractor shall report to Expertise France any faults by the Contractor detected in the course of its mission, or any quality deficiencies attributable to the Contractor, and propose appropriate corrective measures or sanctions.

## Rights and duties of the CONTRACTOR

      - All services and studies necessary for the proper performance of the tasks covered by this Contract shall be deemed included in the scope of the Contractor’s mission, even if not specifically stipulated, unless expressly excluded.

      - The Contractor is bound by a duty to advise on all aspects of their mission. This duty shall be interpreted in the broadest sense and obliges the Contractor to draw the attention of Expertise France to any difficulties or matters falling within their area of expertise.

      - The parties undertake to comply with all applicable legal and regulatory provisions relating to the missions contemplated under this Contract, including civil law rules, technical, safety, urban planning, and construction regulations, as well as any specific requirements or constraints related to the nature of the works.
The Contractor shall keep themselves informed of any changes to applicable standards during the course of the operation and shall immediately notify Expertise France in writing, with appropriate recommendations.

      - Should any requirement from Expertise France result in solutions that do not comply with standard professional practices, or in the selection of a supplier lacking adequate qualifications, or whose commitments fall outside the framework defined by the Contractor (in terms of price, nature, or quality of resources to be implemented), the Contractor shall issue written reservations prior to the implementation of such requirements.

      - The Contractor shall be liable, under general law, for any faults or professional errors relating to the missions covered by this Contract.

      - In the event of any proven fault, error, omission, or inadequacy in the studies, the Contractor shall bear full responsibility for the necessary modifications or corrections to the plans and documents they have prepared.

      - The Contractor undertakes to provide all necessary information to ensure proper understanding of the project by all stakeholders, at any time during the execution of the missions.

      - The Contractor acknowledges their obligation of professional secrecy and confidentiality with regard to all facts, information, studies, and decisions of which they may become aware during the course of the Contract.
In particular, the Contractor shall refrain from any written or verbal communication on these matters, and from sharing any documents with third parties, without the prior written consent of Expertise France.

## 7.5.  Deliverables table

The deliverables are specified in the Technical Specifications, Terms of Reference (TOR) and shall be submitted within the indicated deadlines.
Tacit approval shall not be deemed as an instruction to proceed with the next phase of the mission.

| Item | Deliverable | Submission frequency for the contractor | Delay of Validation for Expertise France |
| --- | --- | --- | --- |
| Phase 1 : Site Assessments, Design Development, and Works Tender Technical Dossier : 30 % from the from the service |  |  |  |
| Mission 1: Preliminary Design Studies (PDS) | • Inception Report; • Assignment Methodology • Site Assessment Report; • Topographical Survey Report; • Geotechnical Investigation Report; • Existing Utilities Assessment Report; • Existing Conditions Assessment Report | After 1 month from the award date | 15 days from date of submission |
|  | • Site visits reports • Design Basis Report; • Applicable Codes and Standards Register • Preliminary Engineering Assessment Report. • Detailed Work Programme • Mobilization Plan | After the 2nd month | 15 days from date of submission |
|  | • Minutes of Meetings and Coordination Records | Monthly | 3 days from date of submission |
| Mission 2: Technical design studies (TDS) | • Architectural drawings. • Structural drawings and structural calculations. • Civil engineering drawings. • Mechanical engineering drawings. • Electrical engineering drawings. • Plumbing and drainage drawings. • HVAC design and calculations. • Water supply and filtration system design, where applicable. • External works and utility interface drawings. • Load calculations and all supporting engineering calculations. • Technical specifications by discipline. • Equipment schedules. • Material schedules. • Design coordination and interface documentation. • General arrangement drawings. • Detailed construction drawings. • Design reports. • Design criteria and basis of design documentation. • Bills of Quantities (BoQs). • Engineer's Cost Estimate. • Tender-ready engineering documentation suitable for procurement and construction. | At the end of the 4th month | 21 days from date of submission |
| Mission 3: Preparation consultation documents (OCD), assistance for the analysis of the bids | • Submission of draft tender technical documents | At the end of 3rd week of the 5th month | 7 days from date of submission |
| Phase 2: Technical Management, Control, and Supervision of Works : 60 % from the from the service |  |  |  |
| Mission 4: VISA for Execution and synthesis studies (VISA) | • Shop Drawing Review Sheets. • Material Submittal Review Sheets. • Method Statement Review Sheets. • Technical Review Comments. • Records of reviewed Contractor submissions. • Technical recommendations related to Contractor submissions. | end of the 8th month from the award date | 15 days from date of submission |
| Mission 5: Works Contract Execution Direction (WED) | • Monthly progress reports including the Technical Management , Control the compliance of the achievements and management: as stated in the MOW technical specification with its supporting documents . | Monthly starting from the 8th month up to 23rd month with total (16 month report "construction implementation period of the project ) | 5 days from date of submission |
| Phase 3 :Provisional Acceptance, Final Acceptance, and Handover : 10 % from the from the service |  |  |  |
| Mission 6: Assistance to reception operations (ARO) | • Provisional Acceptance Inspection Reports. • Punch Lists / Snag Lists. • Defects Verification Reports. • Follow-up Inspection Reports. • Final Acceptance Inspection Reports. • Technical Recommendations for Provisional and Final Acceptance • Administrative documents required for the acceptance of works | End of the 24 th month from the award date | 21 days from date of submission |
| Mission 7: As-Built Documentation (ABD) | • As-Built Drawings (Architectural, Structural, Civil, Mechanical, Electrical and Plumbing). • Final Record Drawings. • Updated Bills of Quantities reflecting the executed Works, where applicable. • As-Built Technical Documentation. • Operation and Maintenance (O&M) Manuals. • Equipment Data Sheets and Manufacturers' Documentation. • Test Certificates and Commissioning Records. • Warranties and Guarantees provided by the Contractor and Suppliers. • Asset Register (where applicable). • Handover Documentation. • Final Close-Out Report. • Soft copies and editable versions of all As-Built Documentation, drawings and supporting documents. | End of the 25 th month from the award date | 30 days from date of submission |

  - Allocation of responsibilities within the consortium

One of the service providers, member of the consortium, is designated in the contract as the representative. He represents all the members before the delegated contracting authority and coordinates the services of the consortium members.

In the case of a joint consortium, the representative is jointly and severally liable with each of the members.

The Contractor undertakes to clearly specify the allocation of roles and responsibilities among the members of the consortium, in accordance with the missions defined in the contract.
The Contractor also undertakes to promptly inform the Contracting Authority of any change affecting this allocation or the composition of the consortium.
Any modification to the composition of the consortium must comply with the conditions set out in the CCAG-MOE.

## Place of execution

The services will be performed in Rawashed region based in Jordan.

## Language of the Contract

This document is written in English, which shall be the reference language for any dispute that may arise regarding the meaning or interpretation of the Contract, to the exclusion of any other language.

## Commitments of the Contractor

The Contractor is subject to a performance obligation and therefore undertakes to:

- comply with the Technical Specifications (Annex 1);

- immediately notify Expertise France in writing of any communication or instruction relating to the services/supplies that it may receive from the Client (beneficiary country or public entity) or from a third party, and not to comply with any such communication or instruction until having discussed the matter with Expertise France and after receiving the latter’s written authorization;

- notify any difficulty it may encounter with the performance of its obligations under the Contract;

- comply with all applicable laws and regulations of the country of delivery of the services/supplies and adopt an attitude and act vis-à-vis third parties in the interests of Expertise France, such that Expertise France cannot be reproached in this regard by the Client, or by any person the latter may have designated;

- protect the interests of Expertise France vis-à-vis the Client;

- act as a loyal advisor vis-à-vis Expertise France;

- present itself vis-à-vis the Client, partners and local authorities as a Contractor engaged by Expertise France;

- apply the undertakings of Expertise France as expressed in its Code of Ethics, provided in Annex 5 of the Contract.

In the context of Contract execution, the Contractor undertakes to:

- perform the services/supplies in a diligent, effective and economic manner, in accordance with generally accepted techniques and practices;

- employ appropriate modern techniques and safe and affective processes.

## Confidentiality

The Contractor shall treat as private and maintain the confidentiality of all documents and information received or which it becomes aware of in the context of the Project. It shall maintain the secrecy thereof and not use them for any purpose other than execution of the Contract.

In this regard, the Contractor undertakes:

- To protect and maintain the confidentiality of information considered or presented as such;

- To handle confidential information it receives with the same degree of care and protection as it applies to its own confidential information;

- only to reveal confidential information to its personnel and third parties involved in performance of the Contract after having received prior written and express approval from Expertise France;

- to take all necessary steps such that its personnel and third parties involved in execution of the Contract, who become aware of confidential information, undertake to treat such information with the same level of confidentiality as set out in this clause;

- As and when required, to reiterate the confidential nature of such information to its personnel and third parties involved in the execution of the Contract, as soon as said confidential information is communicated to the aforementioned persons;

- to reiterate the confidential nature of confidential information prior to any meeting during which confidential information is communicated.

Apart from where necessary for the purposes of service delivery, the Contractor may not disclose any element of the Contract without prior written consent from the other party.

## Provision of documents

Expertise France shall ensure that the Contractor receives in good time all the documents (as set out below) required for delivery of the services:

- Documents 1: Expression of needs from JAF

- Technical Specifications of the Main Contract ToR

## Contact person and communication

All communication and notifications between the Parties under the Contract shall take place in written form, either through the exchange of e-mails or via registered letter with acknowledgement of receipt, where the latter form is prohibited in certain cases under the Contract, and shall be deemed to have been validly served from its receipt by the addressee.

All correspondence shall be forwarded, all carriage costs paid, to the following addresses:

| For Expertise France : | Expertise France Project manager archibald.gallet@expertisefrance.fr 40, boulevard de Port Royal F-75005 PARIS |
| --- | --- |
| For the Contractor: | To be completed by the Contractor (name, e-mail address, physical address) |

Each Party may modify its address at any time subject to notifying the other Party thereof in writing.

## Undertaking against deforestation

Within the framework of the policy to combat imported deforestation and in the hypothesis of the use of raw materials or processed products, the Contractor undertakes to evaluate precisely the quantities really necessary and to study alternatives to the products at risk listed below:

- Meat;

- Eggs ;

- Dairy products ;

- Ready-made meals, margarine, spreads;

- Leather shoes ;

- Automotive upholstery ;

- Household and cleaning products ;

- Agrofuels ;

- Lumber ;

- Solid wood or particle;

- Fuels ;

- Paper ;

- Cardboard ;

- Textiles ;

- Coffee, chocolate ;

- Exotic fruits ;

- Electronics.

For more information, the guide Engaging in Zero Deforestation Public Procurement is available at the following email address : https://www.ecologie.gouv.fr/sites/default/files/Guide_politique_achat_public_zero_deforestation.pdf

- REVIEW CLAUSE

## Modifications Authorized under the Contract

Pursuant to Article R. 2194-1 of the French Public Procurement Code, the provisions of this contract may be subject to review under the conditions set forth in this article.
Modifications may concern the following elements:

- Transition to final remuneration under the conditions defined in Article 1799-1 of the French Civil Code

- Adjustment of the project manager’s studies where variants selected by the delegated contracting authority during the tendering and award of works contracts are retained:
a. Where the delegated contracting authority has decided to allow variants during the tendering of the works contracts and then retained them upon signature, the project manager’s remuneration shall be reviewed if the design studies must necessarily be revised or if a new planning/urbanism authorization is required;

b. In the presence of such variants, the project manager shall indicate, in a document annexed to the bid analysis report, the consequences of their inclusion on his mission and the potential impact on his remuneration, expressed in additional working days according to the daily rates specified in the financial annex to the contract agreement.

- Additional services that have become necessary.

- Circumstances leading the delegated contracting authority to modify the planned methods of awarding and tendering the works contracts.

- Any change in the composition of the consortium. In such case, the project manager shall inform the delegated contracting authority beforehand. This modification is only permitted in exceptional circumstances. The project manager shall submit all documents relating to the bid for approval and acceptance by the delegated contracting authority. Under no circumstances may the modification of the consortium conflict with or result in lower quality than the present contract and the initial competition requirements.

- Consequences of unforeseen events and technical contingencies.

- Phasing of the works or adjustment of study deadlines, not attributable to the project manager.

- Conditions for the coverage of the project manager’s share of the ten-year liability insurance.

- The delegated contracting authority reserves the right to subsequently award the project manager, pursuant to Article R. 2122-7 of the French Public Procurement Code, one or more new contracts for the performance of similar services. Such new contracts may only concern the strict repetition of services described in the present contract documents and relating to the same construction project, in accordance with the initial design. The period during which such new public contracts may be awarded shall not exceed three years from the notification of the present contract.

- Any price adjustments agreed between the parties. The price adjustment formula shall be agreed between the parties according to the index applicable in the contractor’s sector of activity. The price adjustment may be applied annually, where appropriate, but shall not exceed a maximum of 3% of the initial contract amount.

- In addition to Articles 5.2.2, 6.2, and 7.2 of the CCAG MŒ, in the event of changes during contract performance in legislation and/or regulations relating to the protection of personal data, labor protection and working conditions, and/or environmental, health, and safety protection, any modifications requested by the delegated contracting authority’s representative to ensure compliance with the new rules shall give rise to an amendment to the contract or, failing agreement between the parties, to a unilateral modification by the delegated contracting authority.

Modifications provided for under points 1, 2, 3, and 4 are governed by Articles 7.2 and 7.3 below.

At the request of the delegated contracting authority, certain modifications during contract performance shall only be considered after a meeting between the parties.

## Classification of Modifications during the Study Phase

If, during the performance of the project management contract, the delegated contracting authority decides on program modifications affecting the scope of the project, their financial impact on the estimated cost of the works must be assessed by amendment, within the limits set out below.

During the study phase, modifications in the scope of the project or in the estimated cost are classified by the delegated contracting authority into one of the following three categories:

- Category 1 – Modifications to the scope of the project introduced by the project manager during design due to unforeseen circumstances or inaccuracies in his studies.
→ The financial impact of Category 1 modifications may in no case justify an adjustment of the estimated cost of the works or an increase in the project manager’s remuneration.

- Category 2 – Modifications to the scope of the project resulting from changes to the program. Such modifications may be requested by the contracting authority or accepted by the contracting authority upon proposal by the project manager, in order to:

o reasonably improve the quality-price ratio of the services; or
o carry out services essential for the proper completion of the project in accordance with best practice.

- Category 3 – Modifications to the scope of the project imposed on both the contracting authority and the project manager due to external conditions (e.g. changes in regulations or unforeseen technical contingencies, notably archaeological).

  - → The financial impact of Category 2 and Category 3 modifications: when these modifications occur during the studies, their cost shall be assessed by the project manager based on the economic conditions of month M0 of this contract.

  - → The financial impact of Category 2 and Category 3 modifications shall be incorporated into the estimated cost of the works. The project manager’s remuneration shall be adjusted accordingly.

  - → Modifications falling under Category 2 are limited to 10% of the contract amount.

  - Classification of Modifications during the Works Phase

When the works contracts are modified, the project manager shall complete a monitoring document listing the modifications resulting in decreases or increases in value, their amounts, and their potential impact on the completion deadlines. The project manager shall propose to the delegated contracting authority their classification into one of the following three categories:

- Category 1 – Modifications initiated by the delegated contracting authority corresponding to a program change. In this case, the classification shall identify the delegated contracting authority as the originator of the modification.

- Category 2 – Modifications imposed on the delegated contracting authority due to new and unforeseeable elements at the time of signature of the works contracts.
→ Category 1 and Category 2 modifications may give rise to an amendment of the project management contract only insofar as they constitute additional work for the project manager, under the conditions set out in Article 7.1 of this contract. These modifications may be implemented by service orders. However, all service orders with financial implications shall be regularized by amendment.

- Category 3 – Modifications initiated by the project manager resulting from errors and omissions attributable to him, including any economic adjustments accepted by the delegated contracting authority to compensate for such errors or omissions.
→ Category 3 modifications shall not give rise to any adjustment of the project manager’s remuneration.

- ENGAGEMENT OF THE PROJECT OWNER

  - Before the award of the works contracts

Financial envelope set by the Contracting Authority:
This financial envelope allocated to the works includes all works necessary for the implementation of the program.

Provisional estimate of the forecast cost of the works:
As the studies progress, the project manager, when preparing the deliverables of each stage, must verify that the project remains within the commitment made regarding the forecast cost of the works.

Estimate of the forecast cost of the works drawn up by the project manager and commitment:
The forecast cost is the sum of the works amounts for which the project manager is responsible under his assignment and which are necessary for the completion of the project.
It is expressed in terms of the month M0 of the project management contract as defined in Article 3.1 of the Contract Agreement.
The final estimate is subject to a 5% tolerance rate.
Tolerance threshold = forecast cost of the works * (1 + tolerance rate).

Whenever the project manager finds that the project he has designed does not allow compliance with this tolerance threshold—even before knowing the results of the tendering process for the works contracts—he must revise his studies free of charge if requested by the Delegated Contracting Authority.

Consideration of project or cost modifications during the study phase:
If, during the performance of the contract, the Delegated Contracting Authority decides on program modifications leading to changes in the project’s scope, their financial impact on the forecast cost of the works must be assessed, and a new lump-sum fee is then set by amendment, in accordance with Article 8 Review Clause.

Reference cost of works at the outcome of the contractors’ tendering process:
Once the Contracting Authority has the results of the contractors’ tendering process, the project manager establishes the reference cost of the works.
Compliance with this commitment is verified after the initial tendering process, based on the sum of the bids submitted by the contractors and retained by the Delegated Contracting Authority (all lots combined).

Compliance with the project manager’s commitment:
Compliance is assessed on the overall reference cost and not on a lot-by-lot basis.

Consequences of non-compliance with the commitment:
When the reference cost exceeds the tolerance threshold defined above, the Delegated Contracting Authority may:

- either accept the contractor’s offer(s),

- or request that the project manager revise part of the studies in order to adapt the project, within the program’s data, constraints, and requirements, so as to reduce the cost.

In this case, in accordance with Article R.2432-3 of the French Public Procurement Code, the revision of the studies shall be carried out without additional remuneration.
In all cases, no financial penalty may be applied at this stage.

  - After the award of the works contracts

Actual cost of the works:
The actual cost of the works is the cost resulting from the works contracts, for which the project manager is responsible under his assignment, entered into by the Contracting Authority for the project’s implementation. It is equal to the sum of the initial amounts of the works contracts.
The actual cost is notified by the Delegated Contracting Authority to the project manager, who undertakes to comply with it.
The actual cost is deemed to be established on the basis of the economic conditions of month M0 of the works contract(s).

Tolerance on the actual cost of the works:
The actual cost of the works is subject to a tolerance rate of 10%.
Tolerance threshold = actual cost of the works * (1 + tolerance rate).

Comparison between actual cost and tolerance:
The final cost determined by the Delegated Contracting Authority upon completion of the works corresponds to the amount, in base prices M0 works, of the works actually carried out under the contracts and amendments, excluding price revisions or updates.

The reference cost is the final cost excluding additional costs not attributable to the project manager, in accordance with Article R.2432-3 of the French Public Procurement Code.

Consequences of non-compliance with the commitment:
If the reference cost exceeds the tolerance threshold defined above, the project manager shall bear a penalty defined as follows:
Penalty amount = (reference cost – tolerance threshold) * t (penalty rate)
t = remuneration rate set in Article 4 of the Contract Agreement multiplied by 2.

However, in accordance with Article R.2432-4 of the French Public Procurement Code, the amount of this penalty shall not exceed 15% of the remuneration for the project management tasks performed after the award of the works contracts.

- RESPONSABILITY

The Contractor shall assume the professional responsibilities corresponding to the tasks that may be assigned to them, as defined by the laws and regulations in force.

The Contractor shall be held liable for any breach of their duty to advise, including with regard to the selection of stakeholders and the use of information provided by Expertise France.

The Contractor shall ensure that no ambiguity or contradiction exists in the contractual documents that could later give rise to liability for either the Contractor or Expertise France.

The Contractor is responsible for ensuring compliance with construction standards and regulations as set out in the applicable laws and regulations in force.

During the execution of the works, the Contractor shall be responsible for ensuring that the works comply with the contractual documents, the administrative construction permits, and all applicable building regulations, such that no dispute may arise retrospectively.

The Contractor may not exempt themselves from liability on the grounds that Expertise France has approved their plans, proposals, or the progress of the various phases of the construction.

The Contractor shall inform Expertise France of any new regulations, technical approvals, or professional standards that may come into effect during the performance of the works, and shall propose the necessary adjustments accordingly.

All services shall comply with the provisions of the Contract, with applicable standards and technical specifications being those in force on the date of signature of the Contract.

- INSURRANCE

  - Insurance of the Project manager – Professional Liability Insurance

This policy must cover the financial consequences of the general civil liability that the project manager may incur towards third parties and the client, as a result of any bodily injury, property damage, or consequential loss (whether or not resulting from bodily injury and/or property damage) occurring during or after completion of the works. The project manager shall, at its own expense, take out and maintain civil and professional liability insurance policies covering bodily injury, property damage, and/or consequential loss that may arise from the performance of its services, with a minimum coverage amount not lower than the total budget allocated to the works.

The project manager shall also, at its own expense, take out and maintain insurance policies covering its liability for occupational illness or workplace accidents affecting its staff assigned to the performance of the services.

The project manager further undertakes to subscribe to any insurance policy made compulsory under the regulations applicable at the place where this contract is performed.

The project manager must be able to provide, upon first request by Expertise France, certificates evidencing subscription to the aforementioned insurance policies.

  - Common Provisions

For all other professional liabilities, the project manager may not, under any circumstances, be held liable, jointly or severally, for damages attributable to other parties involved in the project.
The project manager shall bear the financial consequences of its liability within the limits of the coverage ceilings set out in its insurance policy.

The occurrence of a loss prior to the completion of the assignment shall not prevent the payment of the project management services.

The project manager’s insurance certificates shall be attached to the contract. The project manager’s professional liability insurance certificate shall be attached to the contract. Where applicable, a professional insurance certificate shall be provided annually, up to and including the year in which the assignment is completed. In the event that the client has taken out optional insurance cover, the client shall provide the relevant certificates or letters of intent issued by its insurer in relation to such policies.

- Similar services

Under Article R.2122-7 of the French Public Procurement Code, the Contractor may be awarded a Contract for similar services to those of the initial contract without advertising or competitive bidding.

- penalties

By derogation from Article 16.2.3 of the CCAG-MOE, in the event of failure to meet the deadlines set out in Article 3.2 of this Contract, the following penalties may be applied:

- Delay in submission of documents

In case of delay attributable to the Contractor in submitting documents, for which deadlines are set in Article 3.2, the Contractor shall incur deductions amounting to €100.00 excl. VAT per calendar day of delay.

- Delay in verification of draft accounts and final account

If the deadlines set in Article 3.2 are not met, the Contractor shall incur a deduction of €100.00 excl. VAT per calendar day of delay. EXPERTISE FRANCE reserves the right to have these verified at the Contractor's expense and risk.

- Delay in processing claims

If the deadline set in Article 3.2 is not respected, the Contractor shall incur deductions amounting to €250.00 excl. VAT per calendar day of delay.

- Absence from a meeting

In case of absence from a meeting convened by EXPERTISE FRANCE, the Contractor shall incur a deduction of €150.00 excl. VAT.

- Delay in processing a subcontracting act

If the deadline set in Article 3.2 is not respected, the Contractor shall incur deductions amounting to €150.00 excl. VAT per calendar day of delay.

- Delay in submission of documents related to change orders

If the deadline set in Article 3.2 is not respected, the Contractor shall incur deductions of €50.00 excl. VAT per calendar day of delay per document.

- Delay in VISA (approval)

If the deadline set in Article 3.2 is not respected, the Contractor shall incur deductions of €50.00 excl. VAT per calendar day of delay per document.

- Delay in proposal for acceptance to Expertise France

If the deadline set in Article 3.2 is not respected, the Contractor shall incur deductions of €100.00 excl. VAT per calendar day of delay.

- Delay in preparation of the reserve clearance report

If the deadline set in Article 3.2 is not respected, the Contractor shall incur deductions of €100.00 excl. VAT per calendar day of delay.

The amount of penalties shall be applied in the calculation of the balance of payments due under the relevant Contract item.
Penalties are cumulative and non-adjustable. The exemption provided for in Article 16.2.1 of the CCAG-MOE shall not apply.

- intellectual property

## Definitions

The Assignment provided for by this article requires definition of the following terms:

- “Result” means any intended outcome of the performance of the Contract which is delivered and definitively accepted by Expertise France;

- “Creator” means any natural person who contributed to the production of the result;

- “Pre-existing right” means any intellectual property right, including pre-existing technologies owned by Expertise France, the Contractor or any third party with a prior interest in the order to be executed under the Contract.

## Ownership of results

The ownership of results, and the title to related intellectual and industrial property rights, including the solutions and technical information they contain, are entirely and irrevocably transferred to Expertise France under the Contract. This Assignment only covers the economic rights of creators under the conditions set out in Article 8.3 of the Contract. The moral rights of creators are excluded. Such moral rights cover the disclosure, paternity and respect for the integrity of the results treated as a work within the meaning of the French Intellectual Property Code.

The aforementioned elements shall be deemed to be effectively transferred to Expertise France after acceptance of the results delivered to it by the Contractor.

The payment of the price to the Contractor is deemed to include any fees payable to the Contractor in relation to the acquisition of rights by Expertise France, notably all forms of exploitation of the results. The acquisition of such covers all territories worldwide.

## Exploitation of results

By acquiring title to the results developed by the Contractor, Expertise France becomes the holder of all economic copyright relating to such rights. In this regard, yet without the list being exhaustive, Expertise France may exploit the results for the following purposes:

- internal exploitation:

  - disclosure to its personnel;

  - communication disclosure to persons and entities working for Expertise France or cooperating with it, including contractors, subcontractors (whether legal or natural persons), EU institutions, agencies and bodies and member states' institutions;

  - installing, uploading, processing, arranging, compiling, combining, retrieving, copying, reproducing in whole or in part and in unlimited number of copies.

- distribution to the public:

  - in paper, electronic or digital format;

  - on the internet as a downloadable/non-downloadable file;

  - via display, radio or television broadcasting or any other transmission technique;

  - otherwise in any form and by any method.

- modifications:

  - modification of content, form or technique;

  - addition of new elements of content and form;

  - adaptation using new media;

  - translation into any language;

  - digitization and computer processing.

## Licensing of pre-existing rights

Expertise France shall not acquire ownership of pre-existing rights. The Contractor shall license the pre-existing rights on a royalty-free, non-exclusive and irrevocable basis to Expertise France, which may use the pre-existing rights as set out in Article 8.3. Such licenses shall become effective from the moment the results are delivered by the Contractor and accepted by Expertise France. On delivery of the results, the Contractor may, as required, provide Expertise France with a list of pre-existing rights and third parties' rights, including those of its personnel, of creators and of other right holders. The licensing of pre-existing rights to Expertise France under the Contract covers all territories worldwide and is valid for the whole duration of intellectual property rights protection.

## Guarantees

When delivering the results, the Contractor shall warrant that they are free of rights or claims from creators and third parties, including in relation to pre-existing rights, for any use envisaged by Expertise France.

On request from Expertise France, the Contractor shall provide evidence of ownership or rights to use all the listed pre-existing rights and rights of third parties, except for the rights owned by Expertise France.

## Image rights

If natural, recognisable persons appear in a result or their voice is recorded, on request from Expertise France the Contractor shall submit a declaration in which such persons (or of the persons exercising parental authority in case of minors) give their permission for the described use of their image or voice. This does not apply to persons whose permission is not required in line with the law of the country where photographs were taken, films shot or audio records made.

- Termination of the CONTRACT

## General terms of performance

The Contract is subject to the termination clauses as defined in Articles 29 to 36 of the CCAG.

By way of derogation from Article 31 of the CCAG MOE, termination for reasons of general interest is not applicable to this Contract. However, the parties agree on the possibility of terminating the Contract by mutual consent.

In the event of early termination, the Contractor shall immediately return to Expertise France all documents it may have received for the purposes of execution of the Contract.

Termination

In addition to the provisions of Articles 25 and 34 of the CCAG-MOE, the termination decision shall be notified by EXPERTISE FRANCE to the Contractor by registered letter with acknowledgment of receipt, or by any other means allowing proof of receipt. The notification shall specify the effective date of termination.

In the event of non-compliance with contractual provisions, and after an unsuccessful formal notice, Expertise France’s representative may terminate the Contract for the sole fault of the Contractor, without any compensation being due.

The Contract may be terminated automatically and without compensation in case of relocation, dissolution, or restructuring of the beneficiary rendering the performance of the service impossible under the conditions provided in the Contract documents.

By way of derogation from Article 31 of the CCAG-MOE, termination may also be exercised automatically for reasons of public interest:

## Procedure

Any termination decision shall be notified by Expertise France to the Contractor by registered letter with acknowledgement of receipt. It shall state the effective date of termination.

- SUSPENSION OF SERVICES IN CASE OF UNFORESEEABLE CIRCUMSTANCES

When the continuation of Contract execution is temporarily rendered impossible due to a circumstance that diligent parties could not have foreseen either in its nature or extent, or due to the issuance by a public authority of measures restricting, prohibiting, or significantly modifying the exercise of certain activities because of such circumstance, the suspension of all or part of the services shall be ordered by Expertise France.

When the suspension is requested by the Contractor, the purchaser shall decide on the validity of this request as soon as possible.

Within a timeframe appropriate to the circumstances and not exceeding fifteen (15) days from the decision to suspend the services, the parties shall agree on the modalities for verifying the services performed and, where applicable, the maintenance of part of the contractual obligations remaining incumbent on the Contractor during the suspension.

Within a reasonable timeframe, the parties shall also agree on the modalities for resuming the execution and, where applicable, on the modifications to be made to the Contract and the allocation of any additional costs directly caused by these events.

Failing an agreement between the parties, the Contractor shall be required, at the end of the suspension, to resume the execution of the services under the conditions set forth in the Contract, and any disagreement shall be resolved in accordance with the provisions of Article 15.1 of the Contract.

- MEASURES TAKEN EX OFFICIO

When the Contractor expressly acknowledges identified breaches, Expertise France may resort to the following measures ex officio:

- unilateral termination of the Contract,

- execution by direct management of all or part of the unperformed Contract,

- the conclusion of one or more contracts with one or more third parties for all or part of the remaining Contract to be executed.

These measures shall be applied at the Contractor’s expense, risk, and peril.

- safety and security measures and responsabilities

The Contractor is the only one who is responsible for the safety of the people and property that he mobilizes for the execution of the present Contract and in this respect, takes all necessary measures. He undertakes to ensure that all of his employees and subcontractors comply with the safety instructions that he issues.

In the event of an incident and/or direct or indirect attack on the safety of people directly or indirectly mobilised by the Contractor or its equipment, Expertise France cannot be held responsible in any way whatsoever.

- ethics

The Contractor also undertakes to take note of the  Expertise France Code of Conduct and to comply strictly with it (the Expertise France code of conduct is available on the agency’s website: www.expertisefrance.fr).

Any breach to comply with the code of conduct may result in the termination of the Contract and incur the liability of the Contractor.

- Administration of personal data

Under Article 13 or Regulation (EU) no. 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data (GDPR), the Contractor is notified that personal data (notably name, first name and e-mail address) collected under this Contract may be processed.

The legal basis under which such processing is performed are set out in c) and e) of Article 6.1 of the GDPR, namely:

- The processing is necessary in order to comply with a legal obligation by which Expertise France is bound;

- The processing is necessary for performance of a public-interest assignment or which falls within the scope of the public authority entrusted to Expertise France.

The purposes of the processing are as follows:

- Management and monitoring of this Contract

- Management and monitoring of reports forwarded to donors and other supervisory authorities.

Recipients or category of recipients of the personal data are exclusively authorised personnel of Expertise France, ministries and state operators and donors responsible for awarding and executing this Contract, including any service providers assisting them with their activities.

Retention period: the data will be held throughout the execution of the Contract, including the DUA (duration of administrative usefulness) applicable to the Contract.

Under Articles 15 to 21 of the GDPR, persons whose personal data is collected enjoy a right of access, rectification and deletion with regard to such data. They also enjoy the right to restrict and refuse processing on legitimate grounds. The information and other rights of data subjects may be exercised by contacting the Data Protection Officer of Expertise France (informatique.libertes@expertisefrance.fr).

Persons whose personal data is collected under this procedure may submit a complaint to CNIL.)]

The Contract may require the processing of personal data. The parties undertake to comply with regulations on the processing of personal data in accordance with amended law no. 78-17 of 6 January 1978 relating to data processing, files and liberties and regulation (EU) 2016/679, known as the General Data Protection Regulation (GDPR).

The Contractor notably undertakes to:

- Process personal data solely for the purposes of the Contract, as defined in annex hereto covering the collection of personal data (GDPR data processor);

- Ensure that persons authorised to process personal data undertake to maintain its confidentiality or are bound by an appropriate legal obligation of confidentiality;

- Implement appropriate technical and organisational measures to guarantee a level of security commensurate with the risks resulting from the Contract, notably with regard to data encryption, confidentiality and integrity;

- Notify Expertise France, via any means, of any personal data breach within 24 hours of becoming aware of any such event;

- Assist Expertise France in its obligation to respond to requests it may receive from data subjects;

- Delete all personal data or return it to Expertise France on conclusion of the services covered by the Contract, as specified by the latter, unless EU law or that of the member state requires such data to be retained;

- Make available to Expertise France all information it may require to demonstrate compliance with the obligations set out in this article and to enable audits to be conducted by the latter or by any other person of its choice.

Where the Contractor uses a data processor to process personal data during execution of the Contract, it must obtain prior written authorisation from Expertise France. Similarly, the Contractor shall notify Expertise France of any planned change concerning the addition or replacement of processors, thereby enabling Expertise France to issue any objections it may have in this regard.

The same obligations concerning data protection as those set out in the Contract are mandatory for processors, notably regarding the provision of adequate guarantees for the implementation of appropriate technical and organisational measures ensuring the protection of personal data. Should any processor fail to meet its obligations, the Contractor shall remain fully responsible vis-à-vis Expertise France for the fulfillment of the processor’s obligations.

In the event of non-compliance with the aforementioned provisions, the Contractor is reminded that its liability may be invoked. In the event of any breach of professional secrecy or non-compliance with the aforementioned provisions, Expertise France may immediately terminate the Contract without compensation for the Contractor.]

- Dispute resolution - applicable law

Any dispute between the Parties relating to the existence, validity, interpretation, execution, and termination of the Contract (or any of its clauses) that the Parties cannot resolve amicably within 30 days of the notification of the dispute by the requesting Party to the other Party, shall be submitted to the competent court.

The applicable law for this Contract is French law, to the exclusion of any other law.

- Derogation from the CCAG

The following articles of this document derogate from the CCAG-MOE:

- Article 4.11 derogates from article 10 of the CCAG ;

- Article 12 derogates from article 16.2.3 of the CCAG ;

- Article 14 derogates from article 31 of the CCAG ;

- AUDIT

The Contractor may be submitted to an audit concerning compliance with the regulations and contractual obligations applicable to the performance of the present Contract. This audit may be carried out by Expertise France or by a third party appointed by Expertise France and may not be refused by the Contractor. If the audit is carried out by a third party, the appointed third party must not be a direct competitor of the Contractor. Scheduled audits may be carried out periodically or spontaneously at the request of Expertise France or a third party. In all cases, the contractor will be informed at least 5 working days in advance.

The Contractor therefore undertakes to:

- Allow Expertise France or the appointed entity, and facilitate their access to the information required to carry out the audits, including interviews with the people involved and on-site visits;

- Submit documents relating to the performance of the present Contract as well as any documents required by the auditors;

- Demonstrate transparency and respond to auditors’ requests;

- Implement any corrective measures that may be necessary.

Expertise France will notify the Contractor of the identity of the audit structure selected in the case of an external firm, the purpose of the assignment, the planned duration of the assignment and the names of the experts assigned.

The Contractor also undertakes to allow Expertise France, or any other third party mandated by Expertise France, to carry out an investigation in the case of an allegation of a prohibited practice relating to the present Contract, under the conditions set out above.

The conclusions of the audit report will be sent to each of the Parties by any means deemed appropriate by Expertise France.

The conclusions may prescribe the implementation of actions and a deadline for completion.

Any refusal by the Contractor to comply with the audit exercises and/or their conclusions gives as of right to Expertise France the possibility to terminate the present Contract without compensation.

- Final provisions

## Declaration

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) hereby declares:

- that no natural or legal person on whose behalf the Contractor is acting is subject to the prohibitions set out in Articles L. 2141-1 to L. 2141-6 and L. 2141-7 to L. 2141-11 of the French Public Procurement Code or any equivalent prohibition issued in another country;

- that the commitments made by the Contractor within the scope of the Contract do not create a situation of conflict of interest that may affect the execution of the Contract;

- that the Contractor have not committed any act that may influence the process of Project implementation to the detriment of the Beneficiary, and notably that no Understanding has been, or will be, entered into;

- that the negotiation, award and execution of the Contract has not given rise to, nor will do so in the future, any act of corruption as defined in the United Nations Convention Against Corruption dated 31 October 2003;

- accepts that the Contract will be awarded in accordance with standard practices and in electronic format.

Furthermore,

The Contractor, its affiliates, suppliers, service providers, consultants and subcontractors (including directors, employees and agents of such entities) certify that:

- they do not acquire and don't supply/will not acquire or supply equipment and do not intervene/will not intervene in sectors under embargo by the United Nations, the European Union or France. For information, the list can be found at: https://www.sanctionsmap.eu ;

- they are not included in the lists of financial sanctions adopted by the United Nations, the European Union, France and/or the United States, notably in the fight against the financing of terrorism and against attacks on national peace and security. For information, the lists can be consulted at the references below:

- for the United Nations, the United Nations Security Council sanctions lists: https://www.un.org/securitycouncil/content/un-sc-consolidated-list;

- for the European Union, the lists can be consulted at the following address: https://www.sanctionsmap.eu;

- for France, see: https://gels-avoirs.dgtresor.gouv.fr/List;

- for the United States, see: https://home.treasury.gov/policy-issues/financial-sanctions/sanctions-programs-and-country-information;

- they are not subject to a World Bank exclusion order and are not on the list published by the World Bank. For information, the list can be consulted at the following address:

https://www.worldbank.org/en/projects-operations/procurement/debarred-firms

In the hypothesis of such a decision of exclusion, we can join to the present declaration on honor the additional information which would allow to consider that this decision of exclusion is not relevant within the framework of the market).

Finally, the Contractor, its affiliates, suppliers, contractors, consultants and subcontractors (including directors, employees and agents of such entities) acknowledge and accept that the above-mentioned situations may lead to the automatic termination of the Contract.

They undertake to inform Expertise France without delay of any change in our situation during the execution of the Contract with regard to the present declaration.

FOR THE Contractor:

In.....………....….., on...…….....20....

Preceded by the handwritten words “Read and approved":

Signature:

Name:
First name:

Role:

FOR EXPERTISE FRANCE:

This offer is accepted as an undertaking.

In.....………....….., on...…….....20....

Signature:

Name:
First name:

Role:

Done in one original copy retained by Expertise France.

# Annex 1: Technical Specifications

This part must be completed if the candidate submits a joint tender on behalf of a group of companies (delete in the case of a tender submitted by an individual candidate).

In the case of a consortium, this section must be completed by the representative. To be duplicated as many times as necessary depending on the number of co-contractors (members of the consortium).

Prohibited practices as defined by the Agence Française de Développement group are defined below: https://www.afd.fr/en/ressources/afd-groups-policy-prevent-and-combat-prohibited-practices-2020

Date and original signatures

Date and original signatures