# Terms of reference 
and technical Specifications

# I.	General information

| Assignment name | Event Management Services for Green Forward Project Activities in Jordan (Policy Dialogue, Webinars, and Capacity Building Trainings) |
| --- | --- |
| Beneficiary | National institutions (sectoral ministries) and regional stakeholders from seven Southern Neighbourhood countries |
| Country | Jordan (Amman) |
| Total number of events | 12 events: 1 Policy Dialogue + 4 Webinars + 7 Capacity Building Trainings (March–November 2026) |

# II.	Context and justification of the need

Expertise France is the French public international cooperation agency. It designs and implements projects that aim to contribute to the balanced development of partner countries, in line with the Sustainable Development Goals (SDGs) of the 2030 Agenda.

The Green Forward project, implemented by Expertise France and funded by the European Union, aims to accelerate the transition to green and circular economies in the Southern Neighbourhood. The project covers seven beneficiary countries: Jordan, Lebanon, Tunisia, Palestine, Morocco, Egypt, and Libya. It operates across three main pillars: regional policy dialogue, knowledge sharing and capacity building, and national-level technical assistance for the development of green and circular economy roadmaps.

As part of the 2026 annual work plan, a series of national and regional activities will be implemented in Jordan. These include one regional policy dialogue, four thematic webinars broadcast from Jordan, and an expanded series of seven national capacity-building training workshops, as identified in the Investment Roadmap Action Plan. This contract seeks to procure comprehensive event management services to ensure the professional and seamless delivery of all logistical and technical arrangements for these activities.

# III.	Objectives and desired results

## 1)	General objective

The objective of the assignment is to provide professional event management services ensuring the successful delivery of all logistical, technical, and administrative arrangements for twelve project activities in Jordan, allowing participants and experts to focus on substantive policy learning and exchange.

## 2)	Specific objectives

Ensure efficient and timely organisation of all logistical arrangements for both in-person events (policy dialogue, capacity building trainings) and virtual events (webinars).

Provide end-to-end logistical coordination before and during all activities, including venue management, catering, participant travel and accommodation, audio-visual and technical support, interpretation services, and on-site staffing.

Ensure compliant financial and administrative management, including documentation and reporting in accordance with Expertise France and EU donor requirements.

Guarantee visibility and communication requirements, ensuring all materials comply with Expertise France and EU visibility guidelines.

Support Expertise France teams on-site and online, facilitating smooth coordination and rapid resolution of any logistical or technical issues.

## 3)	Anticipated results

All twelve events are successfully executed on time, within budget, and with no disruption to the approved agendas.

Participants are well-informed, supported, and able to fully engage in all activities, whether in-person or online.

On-site and virtual logistics are efficiently coordinated, ensuring the smooth running of all sessions, meetings, and workshops.

Communication and visibility materials are produced and deployed in line with EU and Expertise France requirements.

Final technical and financial reports are submitted on time, complete, and audit-ready.

# IV.	Description of the assignment

## 1)	Planned activities

The service provider shall deliver event management services for the following twelve activities, grouped into three categories:

A.	Third Regional Policy Dialogue

Date: End of May 2026 (1 day)

A one-day, in-person regional policy dialogue event to be held in Amman, Jordan. The event will bring together approximately 50–60 senior officials, policymakers, and stakeholders from the seven beneficiary countries to discuss progress on green and circular economy policy alignment and implementation at the regional level.

The service provider shall ensure the following:

Venue: Booking of a suitable hotel conference room or event venue in Amman for approximately 50–60 participants, equipped with a projector, screen, microphones (handheld and delegate), and sound system.

Accommodation: Hotel bookings for international participants (approximately 30–35 persons) for 2 nights (arrival night + event night), on a bed-and-breakfast basis.

Travel: Airport transfers for international participants (grouped pickups/drop-offs at Queen Alia International Airport).

Catering: Two coffee breaks and one lunch on the event day. One welcome dinner on the arrival evening for all participants.

Interpretation: Simultaneous interpretation services in three languages (Arabic, English, French), including two interpreters per day and interpretation equipment (headsets for all participants, booth, microphones).

Communication materials: Production and distribution of participant kits with project branding (folders, notebooks, pens, badges, lanyards, printed agendas) in compliance with EU visibility guidelines. Production of two roll-up banners.

On-site coordination: One dedicated event coordinator on-site throughout the event to manage logistics, welcome participants, coordinate transportation, and support the Expertise France team.

Photography: Professional photographer for the event day.

B.	Four Regional Webinars

A series of four thematic webinars to be broadcast from a professional setting in Amman, Jordan. Each webinar will be approximately 2 hours in duration and will target stakeholders from all seven beneficiary countries as well as international experts.

| Webinar | Title | Date |
| --- | --- | --- |
| Webinar 1 | E-waste & WEEE Management | March 2026 |
| Webinar 2 | Sustainable Food Packaging | June 2026 |
| Webinar 3 | Green Industrial Competitiveness & CBAM | September 2026 |
| Webinar 4 | Textile Waste & Circular Economy | November 2026 |

For each webinar, the service provider shall ensure the following:

Venue/Studio: A professional venue or studio in Amman with reliable, high-speed internet connectivity suitable for live streaming.

Technical production: Setup and management of a virtual webinar platform (e.g., Zoom Webinar or equivalent), including professional AV equipment (cameras, microphones, lighting), a dedicated technician for live production, and screen-sharing capabilities.

Interpretation: Simultaneous interpretation services in three languages (Arabic, English, French) via the virtual platform, including two interpreters per webinar.

Speaker coordination: Technical briefings for speakers prior to each webinar to ensure smooth delivery.

Participant management: Management of online registration, distribution of joining links, and technical support for participants during the live session.

Recording: Full recording of each webinar session for post-event dissemination.

Catering: Light refreshments for the on-site production team and speakers (approximately 5–8 persons).

C.	Seven National Capacity Building Trainings

A series of 7 multi-day (1–2 days each) in-person training workshops to be held in Amman, Jordan. Each training will target approximately 25–30 national stakeholders from Jordanian public institutions, the private sector, and civil society.

| Training | Title | Date |
| --- | --- | --- |
| CB Training 1 | Textile Waste Governance | April 2026 |
| CB Training 2 | Legislative Framework for Green and Circular Economy | May 2026 |
| CB Training 3 | Bankable Investment for Green Economy | June 2026 |
| CB Training 4 | Green Finance Readiness for IRC Members | July 2026 |
| CB Training 5 | Organizational Framework & Investment Facilitation | August 2026 |
| CB Training 6 | Integrated Workshops (Policy, Process, Investment) | September 2026 |
| CB Training 7 | Sustainable Production & Circular Economy for SMEs | October 2026 |

For each capacity building training, the service provider shall ensure the following:

Venue: Booking of a suitable training room in a hotel or conference centre in Amman for 25–30 participants, equipped with a projector, screen, flipcharts, and microphones.

Catering: Two coffee breaks and one lunch per training day.

Training materials: Printing and preparation of training materials, handouts, and participant kits (folders, notebooks, pens, badges) in compliance with EU visibility guidelines.

On-site coordination: One dedicated event coordinator on-site throughout each training to manage logistics, registration, and support the Expertise France team and trainers.

Photography: Professional photographer for each training day.

D.	Cross-cutting services applicable to all activities

Communication materials: All event materials (agendas, presentations, banners, kits) must comply with EU and Expertise France visibility guidelines. Templates will be provided by Expertise France.

Attendance tracking: Collection and submission of signed attendance sheets for all in-person events and participant logs for webinars.

Post-event reporting: Submission of a brief event report for each activity, including key outcomes, attendance data, photos, and financial summary.

Sustainability practices: The service provider is expected to integrate environmentally responsible practices throughout the implementation, including waste reduction, limited use of printed materials and plastics, and sustainable catering options where feasible.

## 2)	Anticipated Deliverables

| Deliverable | Description | End date |
| --- | --- | --- |
| Kick-off meeting | Initial coordination meeting with Expertise France to confirm scope, timeline, and logistics for all 8 events | T0 + 3 days |
| Consolidated logistical plan | Comprehensive plan covering all 8 events with timelines, vendor details, and contingency measures | T0 + 10 days |
| Communication materials | All materials (agendas, kits, banners, signage) for each event | 15 days before each event |
| Booking confirmations | Written confirmation of all venue, accommodation, travel, and vendor arrangements | 20 days before each event |
| Event-specific running orders | Detailed day-by-day running order for each event | 10 days before each event |
| On-site/online coordination | Smooth execution and coordination during each event | During each event |
| Final consolidated report | Technical and financial report covering all activities, with invoices and supporting documents | 15 days after the final event |

## 3)	Coordination

The service provider shall designate a single contact person for project implementation purposes.

Ms Dina Kattan, Implementing Expert will be the service provider's sole contact person for Expertise France.

Tel: 00962790173607

E-mail: dina.kattan@expertisefrance.fr

A launch meeting shall be held within three days after the contract award has been notified. Close collaboration must take place with the Expertise France team from assignment preparation right up to completion. Regular exchanges must take place with the project team on assignment progress and any difficulties that may be encountered.

# V.	Place, duration and terms of performance

All services will be performed in Amman, Jordan. The contract will cover the period from March 2026 to December 2026, encompassing the full lifecycle of all eight planned events.

The provisional schedule for the activities is as follows:

| Activity | Type | Expected Date |
| --- | --- | --- |
| Webinar 1: E-waste & WEEE Management | Virtual (broadcast from Jordan) | March 2026 |
| CB Training 1: Textile Waste Governance | In-person (Amman) | April 2026 |
| CB Training 2: Legislative Framework | In-person (Amman) | May 2026 |
| Policy Dialogue Event 3 | In-person (Amman) | End of May 2026 |
| Webinar 2: Sustainable Food Packaging | Virtual (broadcast from Jordan) | June 2026 |
| CB Training 3: Bankable Investment | In-person (Amman) | June 2026 |
| CB Training 4: Green Finance Readiness | In-person (Amman) | July 2026 |
| CB Training 5: Organizational Framework & Investment Facilitation | In-person (Amman) | August 2026 |
| CB Training 6: Integrated Workshops | In-person (Amman) | September 2026 |
| Webinar 3: Green Industrial Competitiveness & CBAM | Virtual (broadcast from Jordan) | September 2026 |
| CB Training 7: Sustainable Production & Circular Economy | In-person (Amman) | October 2026 |
| Webinar 4: Textile Waste & Circular Economy | Virtual (broadcast from Jordan) | November 2026 |

Service Provider Profile

The service provider should be an established event management company based in Jordan with the following characteristics:

Proven experience managing both in-person and virtual events (minimum 3 years).

Background working with international organizations and development projects.

Familiarity with EU visibility and reporting requirements.

Capacity to manage multiple events concurrently over an extended period.

Access to professional AV equipment and virtual event platforms.

Qualifications and Competences

Event Management Experience: Proven track record in managing complex events with logistics coordination, venue setup, and on-site management.

Virtual Event Expertise: Demonstrated capacity to produce and manage professional webinars and virtual conferences.

Communication Strategy Expertise: Ability to implement communication strategies aligned with EU visibility guidelines.

Team Leadership: Capacity to lead and coordinate teams ensuring timely delivery and seamless event execution.

Technical Resources

The service provider must have access to:

Professional Interpretation Equipment: Simultaneous interpretation system with headsets and receivers for 3 languages (Arabic, English, French).

Audio-Visual Equipment: High-quality microphones, speakers, projectors, screens, cameras, and lighting for both in-person and virtual events.

Virtual Event Platform: Professional webinar platform (e.g., Zoom Webinar) with interpretation channels, recording, and participant management capabilities.

Event Management Software: Registration and attendance tracking systems.

Communication Tools: Laptops, internet connectivity, video conferencing capabilities.

Sustainability Practices

Waste Minimisation: Use reusable materials, digital invitations, and electronic distribution to minimize paper usage.

Sustainable Catering: Source locally produced, organic, and seasonal food options with minimal single-use plastics.

Digital Materials: Prioritize digital formats for presentations, reports, and handouts.

Response Format and Required Documentation

All proposals should be electronically generated. Applicants must submit:

Technical Proposal: Letter of Interest explaining suitability and methodology.

Evidence of Similar Projects: Examples of successfully completed events of similar nature.

Team CVs: Personal CVs highlighting relevant qualifications and experience.

Work References: Minimum three references with contact details.

Financial Proposal: All-inclusive fixed cost bid with breakdown per activity and per cost category.

# VI.	Assignment reports

A consolidated final report, following the model provided by Expertise France, must be forwarded by e-mail on conclusion of the final activity. The report must include a detailed breakdown of costs per activity and all relevant annexes, including attendance sheets, photographs, participant feedback summaries, and financial documentation.

# VII.	Monitoring-evaluation

Performance indicators

| Deliverables | Immediate effects | Intermediate effects | Verification sources |
| --- | --- | --- | --- |
| Consolidated logistical plan | All events are clearly planned and validated in advance | Reduced operational risks and smoother implementation | Approved logistical plan, email validation from EF |
| Communication and visibility materials | Participants receive clear, timely and compliant information | Improved participant preparedness and visibility of the action | Final materials, visibility checklist, participant kits |
| Booking confirmations | All venues, travel, and vendors secured before each event | Events proceed without disruption | Booking confirmations, venue contracts, travel itineraries |
| On-site/online coordination | Efficient day-to-day coordination during each event | Smooth execution and high participant satisfaction | Attendance sheets, daily coordination notes, EF validation |
| Final consolidated report | Clear and complete reporting of all activities and expenses | Financial transparency and accountability | Approved report, financial spreadsheet, annexed invoices |

# VIII.	Practical information

# Evaluation Methodology

The contract will be awarded based on the best value for money principle, according to the following weighting:

| Evaluation Component | Weighting |
| --- | --- |
| Technical Proposal | 70% |
| Financial Proposal | 30% |
| Total | 100% |

A minimum technical score of 42/70 is required for the financial proposal to be opened and considered.

Only bidders achieving the minimum technical threshold will proceed to the financial evaluation stage.

| Sub-criteria for assessing the technical quality | Assessment elements | Scoring guidance | Maximum points |
| --- | --- | --- | --- |
| 1. Understanding of the context and objectives | Understanding of the Green Forward project, EU-funded context, regional and multi-country coordination requirements, and objectives of the assignment. | - Excellent understanding with clear alignment to project objectives and regional implementation context = 8–10 points - Good understanding with minor gaps = 5–7 points - Limited understanding or generic proposal = 0–4 points | 10 |
| 2. Quality of project organization and methodology | Quality and feasibility of methodology, implementation plan, milestones, coordination mechanisms, timelines, contingency planning, and booking management. | - Comprehensive and professional methodology with realistic timelines, detailed milestones, contingency measures, and clear implementation structure = 16–20 points - Methodology generally adequate but lacking detail in some operational aspects = 10–15 points - Weak or incomplete methodology with unclear implementation approach = 0–9 points | 20 |
| 3. Quality and relevance of the proposed logistical arrangements and service delivery | Quality and completeness of logistical arrangements including venue, travel, accommodation, transportation, AV/IT setup, webinar production, interpretation, registration, catering, communication materials, and responsiveness. | - Full logistical coverage with high-quality technical details and clear operational arrangements = 16–20 points - Adequate logistical proposal with some missing or unclear elements = 10–15 points - Incomplete logistical arrangements or weak service delivery approach = 0–9 points | 20 |
| 4. Quality and suitability of the proposed team | Qualifications, CVs, organizational structure, focal points, staffing capacity, and relevant experience managing regional or international events. | - Team demonstrates strong relevant experience (minimum 3–6+ years), qualified focal points, sufficient staffing, and regional/international event experience = 10–12 points - Team generally suitable but with moderate gaps in experience or staffing = 6–9 points - Insufficient experience, weak staffing structure, or incomplete CVs = 0–5 points | 12 |
| 5. Risk management and adaptability | Ability to identify risks and propose mitigation measures related to logistics, schedule changes, technical issues, participant coordination, and operational delivery. | - Strong and realistic risk mitigation strategy with flexibility and adaptability measures = 6–8 points - Basic risk management approach with limited detail = 3–5 points - Weak or missing risk management approach = 0–2 points | 8 |
|  | TOTAL |  | 70 |